## Gantt Chart
Activity Plan · Karan Anand · Jun 2026 – May 2027
Task / Deliverable | Start | End | Jun '26 | Jul '26 | Aug '26 | Sep '26 | Oct '26 | Nov '26 | Dec '26 | Jan '27 | Feb '27 | Mar '27 | Apr '27 | May '27
COMPATIBILITY ANALYSIS OF ENDURANCE | Jun '26 | Mar '27
Requirements Review | Jun '26 | Jun '26
Interface Analysis | Jul '26 | Aug '26
Structural / Thermal Compatibility | Aug '26 | Oct '26
Electrical Compatibility | Oct '26 | Dec '26
SW Integration | Nov '26 | Jan '27
Verification & Validation | Jan '27 | Feb '27
Final Report & Closure | Feb '27 | Mar '27
SYSTEM SIMULATOR DEVELOPMENT | Jun '26 | Aug '26
Design & Architecture | Jun '26 | Jun '26
Development & Integration | Jun '26 | Jul '26
Testing & Delivery | Aug '26 | Aug '26
MISSION ANALYSIS SUPPORT | Jun '26 | May '27
Sloshing Analysis | Jun '26 | Sep '26
Plume Impingement | Jul '26 | Oct '26
Venting & Contamination | Aug '26 | Nov '26
Radiation Analysis | Sep '26 | Dec '26
ESD Analysis | Oct '26 | Jan '27
EMC Analysis | Nov '26 | Feb '27
HFSS Simulation | Dec '26 | Mar '27
ITU Simulation | Feb '27 | May '27